## 90-Day North Star — Sample
M. Alexander & Associates, LLC ¦ From Chaos to Clarity Blueprint™ ¦ Part of the 90-Day Scale Sprint™
90-Day Operating North Star
Mission • Key Metrics • Quarterly Initiatives ¦ Designed for SMBs & Nonprofits
SECTION A — ORGANIZATION OVERVIEW
Organization Name |  |  | Bright Futures Community Services
Quarter / Period |  |  | Q2 2025 (April 1 – June 30)
Prepared By |  |  | Dr. Sandra Williams, COO
Date |  |  | March 28, 2025
SECTION B — 90-DAY MISSION STATEMENT
What is the single most important thing this organization must accomplish in the next 90 days — and why does it matter?
In Q2 2025, Bright Futures Community Services will expand our workforce re-entry program from 3 counties to 5, serving 40% more participants. This expansion is critical to fulfilling our grant commitments and positioning us for the next funding cycle.
SECTION C — KEY METRICS (What does success look like in numbers?)
METRIC |  | BASELINE (NOW) |  | TARGET (90 DAYS) | OWNER |  | TRACKING METHOD
Program participants served |  | 187 / quarter |  | 262 / quarter (+40%) | Program Director |  | Monthly enrollment report
Counties with active programming |  | 3 |  | 5 | Operations Manager |  | County activation tracker
Staff capacity utilization |  | 74% |  | 85% | COO |  | Weekly staffing dashboard
Grant deliverables on-track |  | 68% |  | 90% | Grants Manager |  | Grant compliance log
Client satisfaction score |  | 4.1 / 5.0 |  | 4.5 / 5.0 | Program Director |  | Quarterly survey
SECTION D — FOCUSED QUARTERLY INITIATIVES (3–5 priorities maximum)
# | INITIATIVE |  |  | KEY ACTIONS (this quarter) |  | OWNER | DUE | STATUS
1 | County Expansion — Harford & Cecil |  |  | Execute MOUs with county partners; hire 2 field coordinators; activate intake systems |  | Ops Mgr | May 15 | In Progress
2 | Grant Compliance Overhaul |  |  | Audit all active grants; create compliance calendar; assign deliverable owners per RACI |  | Grants Mgr | Apr 30 | Not Started
3 | Staff Capacity & Scheduling |  |  | Implement new scheduling platform; cross-train 4 staff members; revise workload assignments |  | HR Director | May 31 | Not Started
4 | Client Satisfaction Initiative |  |  | Deploy quarterly survey; analyze Q1 results; implement top 3 service improvements |  | Prog Director | Jun 15 | Planning
5 | Board Reporting Upgrade |  |  | Design new dashboard for board; automate monthly metrics pull; present at June board meeting |  | COO | Jun 1 | Planning
SECTION E — 30 / 60 / 90 DAY MILESTONES
BY DAY 30 |  |  | BY DAY 60 |  | BY DAY 90
County MOUs signed Hiring process launched Grant audit complete |  |  | 2 new counties operational New scheduling system live Q1 survey results analyzed |  | All 5 counties active Grant compliance at 90% Board dashboard live Client score at 4.5
SAMPLE COMPLETED TEMPLATE ¦ © 2025 M. Alexander & Associates, LLC ¦ 90-Day Scale Sprint™ ¦ From Chaos to Clarity Blueprint™ ¦ iwillassistyou.net